## Sheet1
Iteration | Component | Task | Deadline | Notes | Team member
Iteration one follow-ups | Web Pages Design | Detailed UI/UX design (wireframe diagram) | 2024-09-03 | Should include the design of each page, navigation, color, layout, (font) | Adip
| Web Pages | CSS | 03/09/2024 - by 16/9/2024 | Based on the UI design
Iteration two | Kick-off Meeting | Meeting during Tuesday applied class | 2024-09-03 |  | Everyone
| Web pages Design | Detailed UI/UX design (wireframe diagram) | 03/09/2024 (no later than 05/09/2024) | Should include the design of each page, navigation, color, layout, (font) | Adip
| Emission Analytics | Data collection | 2024-09-05 | Clearly outline (1) how the data should be displayed in the webpage (e.g. the user's emission compared to average emission per person in melbourne) (2) what kinds of data can be displayed and are meaningful to users
| Personal Recommendations | Data collection | 2024-09-05 | Clearly outline (1) What will be the better way to catogorise users into heavy users in each categories (appliances, gas, transportation, solar?) (2) what kinds of data can be displayed and are meaningful to users
| 2ed Meeting | Meeting during Friday applied class | 2024-09-06 | Discuss about the data for emission analytics and personal recommendations functions, and the backend and frontend implementation | Everyone
| Emission Analytics | Data visualisation Backend Frontend | 06/09/2024 - 10/09/2024 | Data visualisation (R?), Backend (Python), Frontend (HTTP, JavaScript) | Hongyi Chloe
| Personal Recommendations | Data visualisation Backend Frontend | 06/09/2024 - 10/09/2024 | Data visualisation (R?), Backend (Python), Frontend (HTTP, JavaScript) | Hongyi Chloe
| Web Pages | CSS | 11/09/2024 - by 16/9/2024 | Based on the UI design
| Environmental Education | Data collection | 2024-09-09 | Collect data(articles?) that can be used ot displayed on the webpage
| 3rd meeting | Meeting during Tuesday applied class | 2024-09-10 | Check the functions and discuss the data for environmental education | Everyone
| Environmental Education | Data visualisation Backend Frontend | 10/09/2024-13/09/2024 | Data visualisation (R?), Backend (Python), Frontend (HTTP, JavaScript) | Hongyi Chloe
| Web Pages | CSS | 14/09/2024 - by 16/9/2024 | Based on the UI design
| 4th meeting | Meeting during Friday applied class | 2024-09-13 | Test all the functions | Everyone
|  | Check all the webpages | 2024-09-16 | Check UI/Test functions | Everyone
|  | Iteration 2 submission | 2024-09-16 |  | Everyone
Iterarion three | Web Pages Design | Detailed UI/UX design (wireframe diagram) | 2024-09-18 | Should include the design of each page, navigation, color, layout, (font) | Adip
| Eco-friendly Resource Map | Data collection | 2024-09-18 | Provide the data that can be used for the map
| Kick-off Meeting | Meeting during Friday applied class | 2024-09-19 |  | Everyone
| Eco-friendly Resource Map | Data visualisation Backend Frontend | 19/09/2024 - 23/09/2024 | Data visualisation (R?), Backend (Python), Frontend (HTTP, JavaScript) | Hongyi Chloe